# Minutes of meeting (25)

Date :	28/11/2001

Time:	11:45 pm

Place :	Room 16E03, Faculty of Informatics, Jordanstown

Attendees : Prof. Paul Mc Kevitt, Dr. Paul Hanna, Nazlia Omar

Discussion:

- Dr. Hanna started the discussion by getting some feedback from Prof. Mc Kevitt about the work. In response, he mentioned that he is satisfied with the result and adding that it is good and showing significant contribution.

- Dr. Hanna also asked Prof. Mc Kevitt whether to still consider the semantic analysis at this stage. Prof. Mc Kevitt said that the result may look better with the use of semantic interpretation. He suggested that the semantic issues (analysis, suggestion and problem) may still be included in the writing. The discussion should be included in the end chapter of the thesis to close the loop.

- Prof. Mc Kevitt advised me to get the examples from Gomez as soon as possible as it may take some time for him to respond. In addition, when the time comes for the examples to be tested, they are ready in hand.

- A new schedule has been drafted by both supervisors in order to complete the core work. The plan is outlined as below:

| Task | Duration | Deliverable |
| --- | --- | --- |
| Complete 10 sets of examples – 2 more is needed | A week (to finish by 5/12/01 ) | Applied examples |
| Write algorithms | A week (to finish by middle of week 3-12/12/01) | Algorithms for ER-generator |
| Test (manually) 5 examples | A week (till 19/12/01) | Tested examples |
| Learn Perl | A week (till 26/12/01) |  |
| Write Chapter 3 | In parallel with other tasks | Chapter 3 to be completed and handed in to both supervisors by end of January |
| Implementation | A month – to finish by February | Completed implementation of system |
| Test 5 examples on completed system | A week – till 7/3/02 | Tested examples and result |
| Test Gomez’s examples (around 30) | A month – till 7/4/02 | Tested examples and result |
| Literature survey | A week – till 14/7/02 |  |
| Write Chapter 4 | In parallel with other tasks | Chapter 4 to be completed and handed in to both supervisors by end of April |
| Write paper | In parallel with other tasks | Written paper by end April/beginning May |

- Both the supervisors stressed the importance of successfully completing all the required tasks as they are the core of the research (from present till April). Failing to do so may hamper the chance of getting the PhD.

- Prof. Mc Kevitt also talked about writing for publications. He said that the undergoing research can fit into some international AI journals and conferences like Journal of AI Review (JAIR) and others. He will keep abreast of any coming conferences (to be held in 2002).

The meeting ended at around 2:00 am.

Prepared by:  Nazlia Omar